## Sheet1
Risk | Probability | Impact | Response | Actions
Delay in data handover | H | H | Accept/Mitigate | Reuse of transformed existing data, web resources
\texttt{pycine} library is unusable due to lack of maintenance and documentation. | L | H | Monitor | Manual exportation using Phantom Cine Control (PCC), additional hard drive space, compute power and crash the work-flow to allow for additional time requirement
Image processing is too computationally heavy | M | H | Monitor/Mitigate | Increase the cloud compute resource and/or reduce resolution and/or reduce the dataset size
Training is more computationally intensive than estimated | M | H | Mitigate | Use of sparse network topology techniques(Fast-CNN, Faster-RNN), Increase the cloud compute resource and/or reduce the dataset size
Personnel Crisis during parallel segments | L | H | Mitigate | Reduction of scope
Data loss | L | H | Avoid | Multiple secondary and primary backups, no write operations to the video data.